## Academic
Generic Assessment Program Planning Calendar
| Timing* (Days Out) |  | Schedule (Dates)
Event | Start | Finish | Start | Finish
Conduct Design Conference | -730 | -700 | 2004-03-20 | 2004-04-19
Develop Specifications | -700 | -669 | 2004-04-19 | 2004-05-20
Develop PLLs and PLDs (Draft) | -700 | -669 | 2004-04-19 | 2004-05-20
Review PLLs and PLDs | -669 | -660 | 2004-05-20 | 2004-05-29
Develop Test Items | -669 | -547 | 2004-05-20 | 2004-09-19
ReviewTest Items | -547 | -487 | 2004-09-19 | 2004-11-18
Prepare for Field Testing | -487 | -426 | 2004-11-18 | 2005-01-18
Print/Distribute Field Tests | -426 | -380 | 2005-01-18 | 2005-03-05
Field Test Items | -365 | -350 | 2005-03-20 | 2005-04-04
Score Field Tests | -350 | -319 | 2005-04-04 | 2005-05-05
Analyze Field Test Data | -319 | -304 | 2005-05-05 | 2005-05-20
Review Field Test Item Data | -304 | -274 | 2005-05-20 | 2005-06-19
Draft Standard Setting Plan | -304 | -274 | 2005-05-20 | 2005-06-19
Select Items for Operational Tests | -274 | -243 | 2005-06-19 | 2005-07-20
Present Standard Setting Plan to Stakeholders | -273 | -213 | 2005-06-20 | 2005-08-19
Review Standard Setting Plan | -273 | -213 | 2005-06-20 | 2005-08-19
Prepare for Operational Testing | -243 | -182 | 2005-07-20 | 2005-09-19
Finalize Standard Setting Plan | -213 | -182 | 2005-08-19 | 2005-09-19
Set Dates for Standard Setting | -200 | -185 | 2005-09-01 | 2005-09-16
Identify Standard Setting Candidates | -200 | -140 | 2005-09-01 | 2005-10-31
Secure Meeting Site | -185 | -180 | 2005-09-16 | 2005-09-21
Review Operational Tests | -182 | -122 | 2005-09-19 | 2005-11-18
Select Standard Setting Panelists | -140 | -100 | 2005-10-31 | 2005-12-10
Prepare Final PLLs and PLDs | -122 | -91 | 2005-11-18 | 2005-12-19
Print and Distribute Operational Tests | -122 | -15 | 2005-11-18 | 2006-03-05
Notify Standard Setting Panelists | -100 | -95 | 2005-12-10 | 2005-12-15
Finalize Contract with Meeting Site | -60 | -50 | 2006-01-19 | 2006-01-29
Prepare Standard Setting Materials | -30 | 60 | 2006-02-18 | 2006-05-19
Administer Operational Test | 0 | 12 | 2006-03-20 | 2006-04-01
Score Operational Tests | 15 | 61 | 2006-04-04 | 2006-05-20
Follow-Up Letter to Panelists | 20 | 25 | 2006-04-09 | 2006-04-14
Create On-Site Data Analysis Programs | 32 | 43 | 2006-04-21 | 2006-05-02
Create training presentations | 32 | 43 | 2006-04-21 | 2006-05-02
All Panelists Return Housing Forms | 35 | 39 | 2006-04-24 | 2006-04-28
Complete Hotel Arrangements | 39 | 40 | 2006-04-28 | 2006-04-29
Send Rooming List to Hotel | 46 | 46 | 2006-05-05 | 2006-05-05
Analyze Operational Test Data** | 46 | 61 | 2006-05-05 | 2006-05-20
Arrange for Time on Board Agenda | 47 | 49 | 2006-05-06 | 2006-05-08
Rehearse Presentations | 49 | 50 | 2006-05-08 | 2006-05-09
Print all Rating Forms | 54 | 54 | 2006-05-13 | 2006-05-13
Prepare Participant Materials (See Sample Materials List) | 54 | 56 | 2006-05-13 | 2006-05-15
Purchase All Supplies (See Supplies/Equipment) | 55 | 55 | 1900-02-24 | 2006-05-14
Route Copies of Final Plan to all Presenters | 56 | 56 | 2006-05-15 | 2006-05-15
Assemble Panelist Packets | 56 | 56 | 2006-05-15 | 2006-05-15
Secure Equipment | 56 | 56 | 2006-05-15 | 2006-05-15
Conduct fFnal In-House Dry Run | 56 | 56 | 2006-05-15 | 2006-05-15
Check Meeting Rooms | 60 | 60 | 2006-05-19 | 2006-05-19
Attend to Participant Check-In Issues | 60 | 60 | 2006-05-19 | 2006-05-19
Conduct Standard Setting | 61 | 65 | 2006-05-20 | 2006-05-24
Present Results to Stakeholders | 68 | 72 | 2006-05-27 | 2006-05-31
Review/Adopt Cut Scores | 76 | 91 | 2006-06-04 | 2006-06-19
Print/Distribute Score Reports | 91 | 102 | 2006-06-19 | 2006-06-30
* Relative to start of Operational Testing
** <100% of data analyzed by this date. This is sufficient for standard-setting purposes if the sample is well defined and approved in advance by the TAC.
Generic Standard Setting Planning Calendar
| Timing * (Days Out) |  | Schedule (Dates)
Event | Start | Finish | Start | Finish
Draft standard setting plan | -240 | -210 | 2005-08-24 | 2005-09-23 | 0 | 0
Present plan to TAC | -187 | -198 | 2005-10-16 | 2005-10-16 | 0 | 0
Revise plan in accordance with TAC input | -183 | -165 | 2005-10-20 | 2005-11-07 | 0 | 0
Set dates for standard setting | -180 | -170 | 2005-10-23 | 2005-11-02
Secure meeting site | -170 | -160 | 2005-11-02 | 2005-11-12
Review revised plan | -139 | -138 | 2005-12-03 | 2005-12-04 | 0 | 0
Revise plan in accordance with TAC input | -137 | -109 | 2005-12-05 | 2006-01-02 | 0 | 0
Draft achievement level descriptors | -120 | -102 | 2005-12-22 | 2006-01-09 | 0 | 0
Identify potential panelists | -120 | -100 | 2005-12-22 | 2006-01-11
Revise achievement level descriptors | -113 | -95 | 2005-12-29 | 2006-01-16 | 0 | 0
Submit revised standard setting plan | -95 | -95 | 2006-01-16 | 2006-01-16 | 0 | 0
Review and approve revised plan | -94 | -88 | 2006-01-17 | 2006-01-23 | 0 | 0
Select, notify panelists | -90 | -85 | 2006-01-21 | 2006-01-26
Present plan to stakeholders | -85 | -81 | 2006-01-26 | 2006-01-30 | 0 | 0
Revise plan based on stakeholder input | -78 | -60 | 2006-02-02 | 2006-02-20 | 0 | 0
Finalize contract with meeting site | -60 | -50 | 2006-02-20 | 2006-03-02
Submit final comments on plan | -50 | -39 | 2006-03-02 | 2006-03-13 | 0 | 0
Approve plan | -36 | -32 | 2006-03-16 | 2006-03-20 | 0 | 0
Create on-site data analysis programs | -29 | -18 | 2006-03-23 | 2006-04-03 | 0 | 0
Create training presentations | -29 | -18 | 2006-03-23 | 2006-04-03 | 0 | 0
Complete hotel arrangements | -22 | -21 | 2006-03-30 | 2006-03-31 | 0 | 0
Send rooming list to hotel | -15 | -15 | 2006-04-06 | 2006-04-06
Arrange for time on Board agenda | -14 | -12 | 2006-04-07 | 2006-04-18
Rehearse presentations | -12 | -11 | 2006-04-09 | 2006-04-10 | 0 | 0
Print all rating forms | -7 | -7 | 2006-05-13 | 2006-05-13 | 0 | 0
Prepare participant materials (see Sample Materials List) | -7 | -5 | 2006-04-14 | 2006-04-16
Purchase all supplies (see Supplies/Equipment) | -6 | -6 | 2006-04-15 | 2006-04-15 | 0 | 0
Route copies of final plan to all presenters | -5 | -5 | 2006-04-16 | 2006-04-16 | 0 | 0
Assemble panelist packets | -5 | -5 | 2006-04-16 | 2006-04-16 | 0 | 0
Secure equipment | -5 | -5 | 2006-04-16 | 2006-04-16 | 0 | 0
Conduct final in-house dry run | -5 | -5 | 2006-04-16 | 2006-04-16 | 0 | 0
Check meeting rooms | -1 | -1 | 2006-04-20 | 2006-04-20 | 0 | 0
Attend to participant check-in issues | -1 | -1 | 2006-04-20 | 2006-04-20 | 0 | 0
Conduct Standard Setting | 0 | 11 | 2006-04-21 | 2006-05-02 | 0 | 0
Present results to stakeholders | 7 | 18 | 2006-04-28 | 2006-05-09 | 0 | 0
Incorporate stakeholder recommendations | 14 | 25 | 2006-05-05 | 2006-05-16 | 0 | 0
Present results to Board | 28 | 39 | 2006-05-19 | 2006-05-30 | 0 | 0
Draft final report | 14 | 35 | 2006-05-05 | 2006-05-26 | 0 | 0
Review final report | 36 | 40 | 2006-05-27 | 2006-05-31 | 0 | 0
Submit final report | 40 | 42 | 2006-05-31 | 2006-06-02 | 0 | 0
Approve final report | 42 | 14 | 2006-06-02 | 2006-05-05 | 0 | 0
* From start of standard setting
Sample Materials List (Assumes Bookmark Procedure)
Rater Packet Contents
Agenda
Notetaking Guide
Security Agreement Form
Readiness Form
Expense Form
Bookmark
Evaluation Form
Additional Rater Materials
Test Booklet
Answer Document
Scoring Guide
Achievement Level Descriptors (3)
Difficulty-Ordered Test Booklet
Passage/Stimulus Booklet
Replacement materials for packets
Round 1 Summary Table
Round 1 Summary Graph
Round 1 Impact Data Table
Round 1 Impact Data Graphs (2)
Round 2 Summary Table
Round 2 Summary Graph
Round 2 Impact Data Table
Round 2 Impact Data Graphs (2)
Round 3 Summary Table
Round 3 Summary Graph
Round 3 Impact Data Table
Round 3 Impact Data Graphs (2)
Supplies/Equipment
Supplies
Post-Its
Pencils
Pens
Blank transparencies (printable)
Blank Transparencies (write-on)
Overhead markers
Boxes
Tape
Copy paper
White board markers (1 set per room)
White board erasers (1 per room)
Flip charts (1 per room)
Flip chart markers (1 set per room)
Airbills for returning materials
Equipment
Computers (1 per room)
LCD projectors (1 per room)
Printers (1 per room)
Overhead projector
Disks or USB drives for storing data
Cables and connectors
Pencil sharpeners (1 per room)
Photocopier (or arrangements for copying)
Extension cords
Power strips
Spare bulbs
Batteries
Calculators (for math tests, expense forms)
Other
Secure storage site
Work room
Formulas:
Start = D32+[Start]
Start = [Start, row below]-1
Finish = D32+[Finish]
Finish = [Start, row below]-1

## Certification
Generic Certification Test Planning Calendar
| Timing* (Days Out) |  | Schedule (Dates)
Event | Start | Finish | Start | Finish
Conduct Job Analysis | -336 | -304 | 2001-04-02 | 2001-05-04
Set Dates for Standard Setting (Written and Performance) | -301 | -300 | 2001-05-07 | 2001-05-08
SecureAnnual Meeting Site (One Year Out) | -301 | -300 | 2001-05-07 | 2001-05-08
Analyze Job Analysis Results | -301 | -297 | 2001-05-07 | 2001-05-11
Conduct Design Conference | -287 | -283 | 2001-05-21 | 2001-05-25
Develop Test and Item Specifications | -273 | -248 | 2001-06-04 | 2001-06-29
Develop Test Items | -245 | -171 | 2001-07-02 | 2001-09-14
Finalize Contract with Annual Meeting Site | -210 | -207 | 2001-08-06 | 2001-08-09
ReviewTest Items | -161 | -157 | 2001-09-24 | 2001-09-28
Identify Standard Setting Panelists | -161 | -136 | 2001-09-24 | 2001-10-19
Prepare for Field Testing | -154 | -136 | 2001-10-01 | 2001-10-19
Select Standard Setting Panelists | -133 | -129 | 2001-10-22 | 2001-10-26
Field Test Items | -133 | -108 | 2001-10-22 | 2001-11-16
Notify Standard Setting Panelists | -109 | -105 | 2001-11-15 | 2001-11-19
Score Field Tests | -105 | -101 | 2001-11-19 | 2001-11-23
Analyze Field Test Data | -98 | -87 | 2001-11-26 | 2001-12-07
Review Field Test Item Data | -84 | -80 | 2001-12-10 | 2001-12-14
Select Items for WrittenTests | -77 | -73 | 2001-12-17 | 2001-12-21
Notify Candidates of Written Test Administration | -61 | -52 | 2002-01-02 | 2002-01-11
Process Applications for Written Test | -58 | -28 | 2002-01-05 | 2002-02-04
Draft Standard Setting Plan | -42 | -38 | 2002-01-21 | 2002-01-25
Present Standard Setting Plan to Stakeholders | -35 | -35 | 2002-01-28 | 2002-01-28
Review Operational Tests | -35 | -31 | 2002-01-28 | 2002-02-01
Review Standard Setting Plan | -34 | -10 | 2002-01-29 | 2002-02-22
Secure Standard Setting Sites (Both) | -28 | -24 | 2002-02-04 | 2002-02-08
Print and DistributeWritten Tests | -21 | -20 | 2002-02-11 | 2002-02-12
Prepare Standard Setting Materials | -21 | -17 | 2002-02-11 | 2002-02-15
Follow-Up Letter to Panelists (Written Test) | -14 | -12 | 2002-02-18 | 2002-02-20
Finalize Standard Setting Plan | -7 | -3 | 2002-02-25 | 2002-03-01
Administer Written Test | 0 | 4 | 2002-03-04 | 2002-03-08
Score Written Tests | 8 | 9 | 2002-03-12 | 2002-03-13
Analyze Written Test Data | 9 | 10 | 2002-03-13 | 2002-03-14
Set Standards for Written Test | 10 | 11 | 2002-03-14 | 2002-03-15
Present Results to Stakeholders | 14 | 18 | 2002-03-18 | 2002-03-22
Review/Adopt Cut Scores | 21 | 22 | 2002-03-25 | 2002-03-26
Notify Candidates of Results of Written Test | 23 | 25 | 2002-03-27 | 2002-03-29
Notify Candidates of Performance Test Administration | 28 | 32 | 2002-04-01 | 2002-04-05
Process Applications for PerformanceTest | 35 | 46 | 2002-04-08 | 2002-04-19
Administer Performance Test | 64 | 65 | 2002-05-07 | 2002-05-08
Follow-Up Letter to Panelists (Performance Test) | 70 | 71 | 2002-05-13 | 2002-05-14
Score Performance Test | 98 | 100 | 2002-06-10 | 2002-06-12
Analyze Performance Test Data** | 99 | 100 | 2002-06-11 | 2002-06-12
Set Standards for Performance Test | 101 | 102 | 2002-06-13 | 2002-06-14
Present Results to Stakeholders | 103 | 112 | 2002-06-15 | 2002-06-24
Review/Adopt Cut Scores | 115 | 116 | 2002-06-27 | 2002-06-28
Notify Candidates of Results | 117 | 117 | 2002-06-29 | 2002-06-29
Prepare Final Report | 119 | 130 | 2002-07-01 | 2002-07-12
* Relative to Administration of Written Test
Formulas:
Start = D33+[Start]
Finish = D33+[Finish]